## Schedule
[5 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Spring Break | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13
[5 empty] | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun
Item | Description | Role | Start | End | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19
1 | Group Intro and Brainstorming Meeting (Week 8) | Group | 2026-03-06 | 2026-03-06 | bar: Week 8 F
2 | Database Setup | DB | 2026-03-11 | 2026-03-13 | bar: Week 9 W to Week 9 F
3 | Feasibility Report | PM | 2026-03-11 | 2026-03-13 | bar: Week 9 W to Week 9 F
4 | DB Lab Check-In | DB | 2026-03-13 | 2026-03-13 | bar: Week 9 F
5 | Group Meeting (Week 9) | Group | 2026-03-13 | 2026-03-13 | bar: Week 9 F
6 | Feasibility Report (SUBMITTAL DEADLINE) | Group | 2026-03-15 | 2026-03-15 | bar: Week 9 Sun
7 | Spring Break | Group | 2026-03-16 | 2026-03-22 | bar: Spring Break M to Spring Break Sun
8 | API and Front-End Setup | API / FE | 2026-03-23 | 2026-03-27 | bar: Week 10 M to Week 10 F
9 | Group Internal Check-In (Phone Call) | Group | 2026-03-24 | 2026-03-24 | bar: Week 10 T
10 | Professor's In-Class Check-In | Group | 2026-03-27 | 2026-03-27 | bar: Week 10 F
11 | API and Front-End Lab Check-In | API / FE | 2026-03-27 | 2026-03-27 | bar: Week 10 F
12 | Group Meeting (Week 11) | Group | 2026-03-27 | 2026-03-27 | bar: Week 10 F
13 | 95% Web App Development (API and Front-End) | API / FE | 2026-03-28 | 2026-04-03 | bar: Week 10 Sat to Week 11 F
14 | Mobile App Setup | Mobile | 2026-03-28 | 2026-04-03 | bar: Week 10 Sat to Week 11 F
15 | Group Internal Check-In (Phone Call) | Group | 2026-03-31 | 2026-03-31 | bar: Week 11 T
16 | Mobile App Lab Check-In | Mobile | 2026-04-03 | 2026-04-03 | bar: Week 11 F
17 | 95% Web App Completion (Target Internal Deadline) | API / FE | 2026-04-03 | 2026-04-03 | bar: Week 11 F
18 | Group Meeting (Week 12) / 95% Web App Demo | Group | 2026-04-03 | 2026-04-03 | bar: Week 11 F
19 | 100% Web App Development (Front-End) | FE | 2026-04-04 | 2026-04-12 | bar: Week 11 Sat to Week 12 Sun
20 | 100% Web App Completion (Target Internal Deadline) | FE | 2026-04-13 | 2026-04-13 | bar: Week 13 M
21 | 95% Mobile App Development | Mobile | 2026-04-04 | 2026-04-10 | bar: Week 11 Sat to Week 12 F
22 | API Documentation | API | 2026-04-04 | 2026-04-10 | bar: Week 11 Sat to Week 12 F
23 | Group Meeting (Week 13) / 95% Mobile App Demo | Mobile | 2026-04-10 | 2026-04-10 | bar: Week 12 F
24 | Use-Case Diagram and Sequence (or Activity) Diagram | FE | 2026-04-11 | 2026-04-13 | bar: Week 12 Sat to Week 13 M
25 | ERD | DB | 2026-04-11 | 2026-04-13 | bar: Week 12 Sat to Week 13 M
26 | Mobile App Class Diagram | Mobile | 2026-04-11 | 2026-04-13 | bar: Week 12 Sat to Week 13 M
27 | Unit and Integration Test Results | FE / Mobile | 2026-04-11 | 2026-04-13 | bar: Week 12 Sat to Week 13 M
28 | Prototypes / Wireframe (unclear if both are needed) | API (coord) | 2026-04-11 | 2026-04-13 | bar: Week 12 Sat to Week 13 M
29 | 100% Mobile App Development | Mobile | 2026-04-11 | 2026-04-13 | bar: Week 12 Sat to Week 13 M
30 | 100% Mobile App Completion (Target Internal Deadline) | Mobile | 2026-04-14 | 2026-04-14 | bar: Week 13 T
31 | Gantt Chart | PM | 2026-04-14 | 2026-04-14 | bar: Week 13 T
32 | Prepare Draft Presentation | PM | 2026-04-15 | 2026-04-15 | bar: Week 13 W
33 | Group Meeting (Week 14) / Practice Presentation | Group | 2026-04-16 | 2026-04-16 | bar: Week 13 Th
34 | PROFESSOR'S SUBMITTAL DEADLINE | Group | 2026-04-16 | 2026-04-16 | bar: Week 13 Th
35 | Group 7 Presentation Date | Group | 2026-04-17 | 2026-04-17 | bar: Week 13 F
36 | Group Adjourn | Group | 2026-04-17 | 2026-04-17 | bar: Week 13 F

## Misc
No. | Day
1 | M
2 | T
3 | W
4 | Th
5 | F
6 | Sat
7 | Sun

## PRINT 1
[5 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Spring Break
[5 empty] | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun
Item | Description | Role | Start | End | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22
1 | Group Intro and Brainstorming Meeting (Week 8) | Group | 2026-03-06 | 2026-03-06 | bar: Week 8 F
2 | Database Setup | DB | 2026-03-11 | 2026-03-13 | bar: Week 9 W to Week 9 F
3 | Feasibility Report | PM | 2026-03-11 | 2026-03-13 | bar: Week 9 W to Week 9 F
4 | DB Lab Check-In | DB | 2026-03-13 | 2026-03-13 | bar: Week 9 F
5 | Group Meeting (Week 9) | Group | 2026-03-13 | 2026-03-13 | bar: Week 9 F
6 | Feasibility Report (SUBMITTAL DEADLINE) | Group | 2026-03-15 | 2026-03-15 | bar: Week 9 Sun
7 | Spring Break | Group | 2026-03-16 | 2026-03-22 | bar: Spring Break M to Spring Break Sun
8 | API and Front-End Setup | API / FE | 2026-03-23 | 2026-03-27
9 | Group Internal Check-In (Phone Call) | Group | 2026-03-24 | 2026-03-24
10 | Professor's In-Class Check-In | Group | 2026-03-27 | 2026-03-27
11 | API and Front-End Lab Check-In | API / FE | 2026-03-27 | 2026-03-27
12 | Group Meeting (Week 11) | Group | 2026-03-27 | 2026-03-27
13 | 95% Web App Development (API and Front-End) | API / FE | 2026-03-28 | 2026-04-03
14 | Mobile App Setup | Mobile | 2026-03-28 | 2026-04-03
15 | Group Internal Check-In (Phone Call) | Group | 2026-03-31 | 2026-03-31
16 | Mobile App Lab Check-In | Mobile | 2026-04-03 | 2026-04-03
17 | 95% Web App Completion (Target Internal Deadline) | API / FE | 2026-04-03 | 2026-04-03
18 | Group Meeting (Week 12) / 95% Web App Demo | Group | 2026-04-03 | 2026-04-03
19 | 100% Web App Development (Front-End) | FE | 2026-04-04 | 2026-04-12
20 | 100% Web App Completion (Target Internal Deadline) | FE | 2026-04-13 | 2026-04-13
21 | 95% Mobile App Development | Mobile | 2026-04-04 | 2026-04-10
22 | API Documentation | API | 2026-04-04 | 2026-04-10
23 | Group Meeting (Week 13) / 95% Mobile App Demo | Mobile | 2026-04-10 | 2026-04-10
24 | Use-Case Diagram and Sequence (or Activity) Diagram | FE | 2026-04-11 | 2026-04-13
25 | ERD | DB | 2026-04-11 | 2026-04-13
26 | Mobile App Class Diagram | Mobile | 2026-04-11 | 2026-04-13
27 | Unit and Integration Test Results | FE / Mobile | 2026-04-11 | 2026-04-13
28 | Prototypes / Wireframe (unclear if both are needed) | API (coord) | 2026-04-11 | 2026-04-13
29 | 100% Mobile App Development | Mobile | 2026-04-11 | 2026-04-13
30 | 100% Mobile App Completion (Target Internal Deadline) | Mobile | 2026-04-14 | 2026-04-14
31 | Gantt Chart | PM | 2026-04-14 | 2026-04-14
32 | Prepare Draft Presentation | PM | 2026-04-15 | 2026-04-15
33 | Group Meeting (Week 14) / Practice Presentation | Group | 2026-04-16 | 2026-04-16
34 | PROFESSOR'S SUBMITTAL DEADLINE | Group | 2026-04-16 | 2026-04-16
35 | Group 7 Presentation Date | Group | 2026-04-17 | 2026-04-17
36 | Group Adjourn | Group | 2026-04-17 | 2026-04-17

## PRINT 2
[5 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13
[5 empty] | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun
Item | Description | Role | Start | End | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19
1 | Group Intro and Brainstorming Meeting (Week 8) | Group | 2026-03-06 | 2026-03-06
2 | Database Setup | DB | 2026-03-11 | 2026-03-13
3 | Feasibility Report | PM | 2026-03-11 | 2026-03-13
4 | DB Lab Check-In | DB | 2026-03-13 | 2026-03-13
5 | Group Meeting (Week 9) | Group | 2026-03-13 | 2026-03-13
6 | Feasibility Report (SUBMITTAL DEADLINE) | Group | 2026-03-15 | 2026-03-15
7 | Spring Break | Group | 2026-03-16 | 2026-03-22
8 | API and Front-End Setup | API / FE | 2026-03-23 | 2026-03-27 | bar: Week 10 M to Week 10 F
9 | Group Internal Check-In (Phone Call) | Group | 2026-03-24 | 2026-03-24 | bar: Week 10 T
10 | Professor's In-Class Check-In | Group | 2026-03-27 | 2026-03-27 | bar: Week 10 F
11 | API and Front-End Lab Check-In | API / FE | 2026-03-27 | 2026-03-27 | bar: Week 10 F
12 | Group Meeting (Week 11) | Group | 2026-03-27 | 2026-03-27 | bar: Week 10 F
13 | 95% Web App Development (API and Front-End) | API / FE | 2026-03-28 | 2026-04-03 | bar: Week 10 Sat to Week 11 F
14 | Mobile App Setup | Mobile | 2026-03-28 | 2026-04-03 | bar: Week 10 Sat to Week 11 F
15 | Group Internal Check-In (Phone Call) | Group | 2026-03-31 | 2026-03-31 | bar: Week 11 T
16 | Mobile App Lab Check-In | Mobile | 2026-04-03 | 2026-04-03 | bar: Week 11 F
17 | 95% Web App Completion (Target Internal Deadline) | API / FE | 2026-04-03 | 2026-04-03 | bar: Week 11 F
18 | Group Meeting (Week 12) / 95% Web App Demo | Group | 2026-04-03 | 2026-04-03 | bar: Week 11 F
19 | 100% Web App Development (Front-End) | FE | 2026-04-04 | 2026-04-12 | bar: Week 11 Sat to Week 12 Sun
20 | 100% Web App Completion (Target Internal Deadline) | FE | 2026-04-13 | 2026-04-13 | bar: Week 13 M
21 | 95% Mobile App Development | Mobile | 2026-04-04 | 2026-04-10 | bar: Week 11 Sat to Week 12 F
22 | API Documentation | API | 2026-04-04 | 2026-04-10 | bar: Week 11 Sat to Week 12 F
23 | Group Meeting (Week 13) / 95% Mobile App Demo | Mobile | 2026-04-10 | 2026-04-10 | bar: Week 12 F
24 | Use-Case Diagram and Sequence (or Activity) Diagram | FE | 2026-04-11 | 2026-04-13 | bar: Week 12 Sat to Week 13 M
25 | ERD | DB | 2026-04-11 | 2026-04-13 | bar: Week 12 Sat to Week 13 M
26 | Mobile App Class Diagram | Mobile | 2026-04-11 | 2026-04-13 | bar: Week 12 Sat to Week 13 M
27 | Unit and Integration Test Results | FE / Mobile | 2026-04-11 | 2026-04-13 | bar: Week 12 Sat to Week 13 M
28 | Prototypes / Wireframe (unclear if both are needed) | API (coord) | 2026-04-11 | 2026-04-13 | bar: Week 12 Sat to Week 13 M
29 | 100% Mobile App Development | Mobile | 2026-04-11 | 2026-04-13 | bar: Week 12 Sat to Week 13 M
30 | 100% Mobile App Completion (Target Internal Deadline) | Mobile | 2026-04-14 | 2026-04-14 | bar: Week 13 T
31 | Gantt Chart | PM | 2026-04-14 | 2026-04-14 | bar: Week 13 T
32 | Prepare Draft Presentation | PM | 2026-04-15 | 2026-04-15 | bar: Week 13 W
33 | Group Meeting (Week 14) / Practice Presentation | Group | 2026-04-16 | 2026-04-16 | bar: Week 13 Th
34 | PROFESSOR'S SUBMITTAL DEADLINE | Group | 2026-04-16 | 2026-04-16 | bar: Week 13 Th
35 | Group 7 Presentation Date | Group | 2026-04-17 | 2026-04-17 | bar: Week 13 F
36 | Group Adjourn | Group | 2026-04-17 | 2026-04-17 | bar: Week 13 F